Time based work plan and achievement

Up to October/2017

Project Name : Padma Multipurpose Bridge Project.

Ministry/Division/Agency: Ministry of Road Transport and Bridges, Bridges Division, Bangladesh Bridge Authority

| Sl No. | Work Description as per work plan (major work) | Total Achievement |
| --- | --- | --- |
|  |  | (Status) | % |
| 1 | Main Bridge Construction Commencement of Work: November 2014 Finishing Time of Work: November 2018 | Main Bridge: Sl No Pier Nos Pile Nos Completed Bottom Section Driving Completed Top section driving Completed Bottom Concrete Plug Completed Base Grouting Completed Pile Completed Pier Column Remarks 1. River Span of Main Bridge 40 240 90 63 26 24 24 2 Steel Pile 2.P1 & P42 2 16+12 16 16 Bored Concrete Pile 3. Janjira Viaduct 40 193 154 193 2 Partially casting of column no. N-24 (3rd lift), N-28 (2nd lift) 4. Mawa Viaduct 37 172 23 Truss Fabrication: No of Truss span Reached Span No at Construction Site Fabricated Span No at Construction Site Remarks 41 11 7 Fabrication Work is ongoing for the rest of four & another two nos. relevant work is about to end. Construction of Steel member from using steel plate at Workshop in China= 12 Nos (Staying at Mawa ghat for Shipment) and another 7 nos construction work is on going | 51.00 |
| 2 | River Training Work (RTW) Commencement of Work: December 2014 Finishing Time of Work: December 2018 | Mobilization of equipment such as various sizes rock, stone chips, Sylhet sand, cement and other construction materials is going on. Casting of 30,26,555 Nos. concrete blocks out of 1,33,01,248 Nos. has been completed. Dumping of 26,79,619 nos. Geo-bags out of 2,12,75,000 Nos. has been completed. At Mawa site out of 1.8 km river training work from chainage -500m to +900m (1.4 km) 800kg Geo-bag damping has been completed at 5 layer in lunching apron and in trial section at Jajira site from chainage -500m to +140m (680m) 125 kg Geo-bag damping work has been completed successfully. Besides at Mawa site Scour Holes (Void 1 & Void 2) at slope were filled and 125 kg Geo-bag damping work has been completed above them. Moreover 8 nos pond filling work have been completed at embankment zone. At Jajira site trial section from chainage -980m to -400m (580m) 800kg geo bag damping have been completed at 5 layers. Besides 125kg geo bag damping have been completed at 3 layers and in the mean while above those rock damping work has been completed upto 44,910 cubic meters and CC block damping has been completed upto 11,13,354 nos. Rock dumping upgradation work is ongoing now. Besides at Jajira site embankment work from 1+650m to 2+700m is ongoing. Slope Trimming at the countryside of the embankment in being continued and sandy loam placement is also ongoing. At Janjira site from chainage 4+900m to 6+500m (1.2 km) bulk dredging has been completed and from chainage 0+100m to 1+100m bulk dredging is ongoing. Final Trimming work is ongoing from chainage 4+900m to 6+500m. In the meantime, casting of 93,49,887 nos CC half bricks’ out of 5,34,50,500 nos has been completed and the rest of work is ongoing. Besides 14,54,800 nos CC half Bricks dumping was completed. At Mawa site from chainage 100m to 800m embankment work is ongoing. | 34.20 |
| 3. | Construction Supervision Consultant-2 (CSC-2) for Main Bridge & River Training Works Commencement of Work:November 2014 Finishing Time of Work:November 2018 | Supervision of work is going on. | 57.00 |
| 4. | Janjira Approach Road Construction Commencement of Work: October 2013 Finishing Time of Work: June 2017 | Approach Road = 10.637 km, Service Road =9.589 km, link road=5.495km and Connecting Road =4.495 km construction work is ongoing. Construction work of 5 nos Bridge, 20 nos Culvert, 8 nos Underpass as well as Toll Plaza, Police Station & Fire Station is also being continued. | 99.60 |
| 5. | Mawa Approach Road Construction Commencement of Work: January 2014 Finishing Time of Work: July 2016 | Work is substantially complete. | 100 |
| 6. | Service Area-2 Commencement of Work: January 2014 Finishing Time of Work: July 2016 | Work is substantially complete. | 100 |
| 7. | Construction Supervision Consultant-1 (CSC-1) for Approach Roads & Service Area-2 Commencement of Work: October 2013 Finishing Time of Work: October 2017 | Supervision of work is going on. | 94.00 |
| 8. | Land Acquisition | Munshigonj: Proposed land =412.70 hectares; Acquisition land = 331.25 hectares; Possession taken by PMBP = 319.91 hectares. Madaripur: Proposed land = 1213.81 hectares; Acquisition land = 549.85 hectares; Possession taken by PMBP =549.76 hectares Shariatpur: Proposed land = 741.46 hectares; Acquisition land = 591.56 hectares; Possession taken by PMBP = 579.74 hectares # Total proposed land for three districts =2367.97hectares; # Total acquisition land for three districts =1472.66 hectares; # Total Possession of land taken by PMBP in 3 districts =1449.41 hectares. |
| 9. | Resettlement activities (Compensation and plot handed over) | Tk. 621.13 crore additional grants have been handed over to the PAP up to October/2017. 2441 Nos. plots have been handed over to the PAP which is recommended by the “Project Level Plot Allocation Committee” up to October/2017. Among them it has been handed over 628 Nos. of plots to Landless families without any cost. Moreover house development facility has been provided to the 475 nos. affected people. |
| 10. | Environment Activities | a) 1,51,457 Nos. of tree plantation has been completed up to October/2017 in resettlement area, approach road and service area on both side of the river. The maintenance work of the planted trees has been completed in June/2017. Preparation for plantation in approach road is ongoing. b) MoU has been signed with Zoological Department of Dhaka University to stablish a Museum in the project area. For this purpose, proposed signing of contract agreement has been completed. And 1249 nos. sample of species has been collected and preserved till October/2017. c) For “Consultancy Services for Preparing a Comprehensive Documentation of Padma Multipurpose Bridge Project,” negotiation has been signed between Impress telefilm and PMBP on 17/02/2016. According to contact the 1hr video recorded for the first 6 (six) month was received. Monthly progress report is being send regularly. |
| 11. | Management Support Consultancy (MSC) Commencement of Work:February 2016 Finishing Time of Work: February 2019 | Work is ongoing. | 39% |

- Total progress of the project up to 48.00%.