Time based work plan and achievement

Up to September/2017

Project Name : Padma Multipurpose Bridge Project.

Ministry/Division/Agency: Ministry of Road Transport and Bridges, Bridges Division, Bangladesh Bridge Authority

| Sl No. | Work Description as per work plan (major work) | Total Achievement |
| --- | --- | --- |
|  |  | (Status) | % |
| 1 | Main Bridge Construction Commencement of Work: November 2014 Finishing Time of Work: November 2018 | Main Bridge: Sl No Pier No Pile No Completed Bottom Section Driving Completed Top section driving Completed Bottom Concrete Plug Completed Base Grouting Completed Pile Completed Pier Column Remarks 1. River Span of Main Bridge 40 240 77 57 24 24 24 Steel Pile 2.P1 & P42 2 16+12 16 16 Bored Concrete Pile 3. Janjira Viaduct 48 193 143 188 2 Partially casting of column no. N-24 (3rd lift), N-28 (2nd lift) 4. Mawa Viaduct 44 172 09 Truss Fabrication: No of Truss span Reached Span No at Construction Site Fabricated Span No at Construction Site Remarks 41 10 7 Fabrication Work is ongoing for the rest of three Construction of Steel member from using steel plate at Workshop in China= 12 Nos (Staying at Mawa ghat for Shipment) and another 7 nos construction work is on going | 49.00 |
| 2 | River Training Work (RTW) Commencement of Work: December 2014 Finishing Time of Work: December 2018 | Mobilization of equipment such as various sizes rock, stone chips, Sylhet sand, cement and other construction materials is going on. Casting of 33,00,000 Nos. concrete blocks out of 1,33,01,248 Nos. has been completed. Dumping of 26,49,879 nos. Geo-bags out of 2,12,75,000 Nos. has been completed. At Mawa site out of 1.8 km river training work from chainage -500m to +900m (1.4 km) 800kg Geo-bag damping has been completed at 5 layer in lunching apron and in trial section from chainage -500m to +140m (680m) 125 kg Geo-bag damping work has been completed successfully. Moreover 8 nos pond filling work have been completed at embankment zone. At Jajira site trial section from chainage -980m to -400m (580m) 125kg geo bag damping have been completed at 3 layers. Among those rock damping work has been completed upto 40,487 cubic meters and CC block damping has been completed upto 81,575 cubic meters. CC block dumping work is ongoing. Besides embankment work from -980m to 1+500m is ongoing. Laying the geo-textile bag on 200m at river side slope of embankment and 300m at back slope of embankment CC block placement work is ongoing. Including embankment the work of placement of CC block is going on at back slope. At Janjira site from chainage 5+300m to 6+500m (1.2 km) and from chainage 0+700m to 0+900m bulk dredging has been completed. Trimming work is ongoing from chainage 4+900m to 5+100m and from chainage 0-780m to 0-980m. In the meantime, casting of 73,17,175 nos CC half bricks’ out of 5,34,50,500 nos has been completed and the rest of work is ongoing. | 34.00 |
| 3. | Construction Supervision Consultant-2 (CSC-2) for Main Bridge & River Training Works Commencement of Work:November 2014 Finishing Time of Work:November 2018 | Supervision of work is going on. | 55.00 |
| 4. | Janjira Approach Road Construction Commencement of Work: October 2013 Finishing Time of Work: June 2017 | Approach Road = 10.637 km, Service Road =9.589 km, link road=5.495km and Connecting Road =4.495 km construction work is ongoing. Construction work of 5 nos Bridge, 20 nos Culvert, 8 nos Underpass as well as Toll Plaza, Police Station & Fire Station is also being continued. | 99.55 |
| 5. | Mawa Approach Road Construction Commencement of Work: January 2014 Finishing Time of Work: July 2016 | Work is substantially complete. | 100 |
| 6. | Service Area-2 Commencement of Work: January 2014 Finishing Time of Work: July 2016 | Work is substantially complete. | 100 |
| 7. | Construction Supervision Consultant-1 (CSC-1) for Approach Roads & Service Area-2 Commencement of Work: October 2013 Finishing Time of Work: October 2017 | Supervision of work is going on. | 92.00 |
| 8. | Land Acquisition | Munshigonj: Proposed land =412.70 hectares; Acquisition land = 331.25 hectares; Possession taken by PMBP = 319.91 hectares. Madaripur: Proposed land = 1213.81 hectares; Acquisition land = 549.85 hectares; Possession taken by PMBP =549.76 hectares Shariatpur: Proposed land = 741.46 hectares; Acquisition land = 591.56 hectares; Possession taken by PMBP = 579.74 hectares # Total proposed land for three districts =2367.97hectares; # Total acquisition land for three districts =1472.66 hectares; # Total Possession of land taken by PMBP in 3 districts =1449.41 hectares. |
| 9. | Resettlement activities (Compensation and plot handed over) | Tk. 619.35 crore additional grants have been handed over to the PAP up to September/2017. 2423 Nos. plots have been handed over to the PAP which is recommended by the “Project Level Plot Allocation Committee” up to September/2017. Among them it has been handed over 628 Nos. of plots to Landless families without any cost. Moreover house development facility has been provided to the 449 nos. affected people |
| 10. | Environment Activities | a) 87,457 Nos. of tree plantation has been completed up to September/2017 in resettlement area, approach road and service area on both side of the river. The maintenance work of the planted trees has been completed in June/2017. Preparation for plantation in approach road is ongoing. b) MoU has been signed with Zoological Department of Dhaka University to stablish a Museum in the project area. For this purpose, proposed signing of contract agreement has been completed. And 1205 nos. sample of species has been collected and preserved till September/2017. c) For “Consultancy Services for Preparing a Comprehensive Documentation of Padma Multipurpose Bridge Project,” negotiation has been signed between Impress telefilm and PMBP on 17/02/2016. According to contact it was instructed to send the 1hr video recorded for the first 6 (six) month. Monthly progress report is being send regularly. |
| 11. | Management Support Consultancy (MSC) Commencement of Work:February 2016 Finishing Time of Work: February 2019 | Work is ongoing. | 37% |

- Total progress of the project up to 47.50%.